## Backlog
Sprints |  | Stories |  | Task |  | CheckList |  | Est. Time
0 | setup
|  | US-01 | Folder Structure
|  | US-02 | Header
|  | US-03 | Footer
|  | US-04 | Navbar
|  | US-05 | Breadcrump
|  | US-06 | Sidebar
1 | My Requests
|  | US-01 | As a user, I want to see a list of all my event registration requests in the "My Requests" section. | T-01 | Design the "My Requests" layout with space for a list of user requests. | CL-01 | Sidebar is floating | 6 Hours
|  |  |  | T-02 | Develop UI components for displaying request details (request number, status, submission date). | CL-02 | Mockup or design for "My Requests" section completed.
|  |  |  | T-03 | Integrate API calls to fetch user request data from ws_myrequests and request-status endpoints. | CL-03 | UI components for request details designed and implemented.
|  |  |  | T-04 | Populate UI components with fetched user request data dynamically. | CL-04 | API calls to fetch user request data functional.
[6 empty] | CL-05 | User request data displayed correctly in the "My Requests" section.
|  | US-02 | As a user, I want the "My Requests" section to be paginated for large numbers of requests. | T-01 | Design and integrate pagination functionality for the "My Requests" section. |  | Pagination component designed and integrated in "My Requests" section. | 8 Hours
|  |  |  | T-02 | Implement logic to handle user navigation between pages of request listings. |  | Navigation between pages of user request listings functional.
|  | US-03 | As a user, I want to filter my requests by request number, status, and submission date. |  | Design filter options for request number, status, and submission date. |  | Filter UI components designed and implemented within "My Requests" section. | 8 Hours
[5 empty] | Implement logic to handle user selection on each filter option. |  | Logic for handling user selection on filters implemented.
[5 empty] | Update displayed requests based on user-selected filters using API calls. |  | User request filtering based on selections functional.
|  | US-04 | As a user, I want the "My Requests" section to display request number, status, and submission date for each request. |  | Ensure UI components for request number, status, and submission date are implemented within request details. |  | Mockup or design for "My Requests" section completed. | 6 Hours
UI components for request details designed and implemented.
API calls to fetch user request data functional.
User request data displayed correctly in the "My Requests" section.
2 | Events Landing & Event details
|  | US-01 | As a user, I want to click on an "Events" link to see a list of upcoming events. (Events Landing) | T-01 | Design the Events Landing page layout with space for event listings and filtering options. |  | Mockup or design for Events Landing page completed. | 8 Hours
|  |  |  | T-02 | Implement click functionality for the "Events" link to navigate to the Events Landing page. |  | Implemented click event for "Events" link with proper navigation.
|  |  |  | T-03 | Design and implement the Event Details page with registration button. Implement logic to check for past events and disable registration.
|  | US-02 | As a user, I want the Events Landing page to display event details like name, date, image, category, description, and location. (Events Landing) |  | Develop UI components for displaying event details (name, date, image, category, description, location). |  | UI components for event details designed and implemented. | 8 Hours
[5 empty] | Integrate API calls to fetch event data from events_category-listing and events_listing endpoints. |  | API calls to fetch event data functional.
[5 empty] | Populate UI components with fetched event data dynamically. |  | vent data displayed correctly on the Events Landing page.
|  | US-03 | As a user, I want to see a maximum of 6 upcoming events with paging enabled for older events. (Events Landing) |  | Implement logic to filter upcoming events based on today's date. |  | Upcoming event filtering logic implemented. | 8 Hours
[5 empty] | Design and integrate pagination functionality to display a maximum of 6 events per page. |  | Pagination component designed and integrated.
[5 empty] | Develop logic for navigating between pages of event listings. |  | Navigation between event listing pages functional.
|  | US-04 | As a user, I want to filter events by date, category, or available tickets. (Events Landing) |  | Design filter options for date, category, and available tickets. |  | Filter UI components designed and implemented. | 6 Hours
[5 empty] | Implement logic to handle user selection on each filter option. |  | Logic for handling user selection on filters implemented.
[5 empty] | Update displayed events based on user-selected filters using API calls. |  | Event filtering based on user selections functional.
|  | US-05 | As a user, I want events to be sorted by date in ascending order. (Events Landing) |  | Implement logic to sort event data by start date in ascending order before displaying it. |  | Event data sorting logic implemented (ascending order by start date).
|  | US-06 | As a user, I want to click on an event name to see its detailed information on a separate page. (Event Details) |  | Design the Event Details page layout with space for detailed event information. |  | Mockup or design for Event Details page completed. | 12 Hours
[5 empty] | Implement click functionality for event names to navigate to the corresponding Event Details page. |  | Implemented click event for event names with proper navigation.
[5 empty] | Pass the selected event ID as a parameter when navigating to the Event Details page. |  | Parameter passing for selected event ID functional.
|  | US-07 | As a user, I want the Event Details page to display additional information like end date and event tickets. (Event Details) |  | Develop UI components for displaying additional event details (end date, event tickets). |  | UI components for additional event details designed and implemented. | 12 Hours
[5 empty] | Update API calls to fetch additional event data if needed for the Event Details page. |  | API calls updated to fetch additional data (if needed).
[5 empty] | Populate UI components with fetched event details dynamically. |  | Additional event details displayed correctly on the Event Details page.
|  | US-08 | As a user, I want a "Register Now" button to register for an event, redirecting me to the registration page. (Event Details) |  | Design and implement the "Register Now" button on the Event Details page. |  | "Register Now" button designed and implemented. | 4 Hours
[5 empty] | Implement click functionality for the button to navigate to the registration page. (Functionality for registration flow developed separately) |  | Button click functionality with navigation to registration page functional.
|  | US-09 | As a user, I shouldn't be able to register for events that have already passed. (Event Details) |  | Implement logic to disable or popup message |  |  | 4 Hours
3 | Workspace Dashboard
|  | US-01 | As a user, I want to see a Workspace Dashboard displaying statistics about my event requests. |  | Design the Workspace Dashboard layout with sections for request statistics. |  | Mockup or design for Workspace Dashboard completed. | 8 Hours
[5 empty] | Implement API calls to fetch workspace data from ws_dashboard and request-status endpoints. |  | API calls to fetch workspace data functional.
[5 empty] | Display the count of in-progress requests, pending tasks (if applicable), and latest requests. |  | Request statistics displayed correctly on the Workspace Dashboard.
|  | US-02 | As a user, I want the Workspace Dashboard to show the count of in-progress requests, pending tasks, and the latest 5 requests. |  | Develop UI components to display counts for in-progress requests and pending tasks (if applicable). |  | UI components for request counts and latest requests designed and implemented. | 6 Hours
[5 empty] | Develop a section to display the latest 5 requests with UI components for request details |  | Latest request data fetched and displayed correctly.
Populate UI components with fetched request data dynamically.
|  | US-03 | As a user, I want to access a workspace side menu with options for "My Requests" |  | Design the workspace side menu layout with options for "My Requests" and "My Tasks". |  | Workspace side menu designed and implemented. | 6 Hours
[5 empty] | Implement click functionality for each side menu option. |  | Click functionality for side menu options implemented.
[5 empty] | Navigate to the "My Requests" section upon clicking the corresponding menu option. |  | Navigation to "My Requests" section functional.
3 | Registration Request details page | US-01 | As a user, I want to see detailed information about a specific registration request. |  | Design the Registration Request Details page layout with space for displaying all request information. |  | Mockup or design for Registration Request Details page completed. | 8 Hours
[5 empty] | Implement logic to fetch details of the selected request using its ID (passed as a parameter). |  | Logic for fetching specific request details based on ID implemented.
[5 empty] | Develop UI components to display fetched request details (similar to "My Requests" details). |  | UI components for detailed request information designed and implemented.
[5 empty] | Populate UI components with the specific request's data dynamically. |  | Specific request details displayed correctly on the Registration Request Details page.
|  | US-02 | As a user, I want the registration request details page to be read-only except for a "Cancel" button. |  | Implement logic to disable editing of all request details on the page. |  | Editing functionality for request details disabled. | 4 Hours
[5 empty] | Design and implement the "Cancel" button. |  | "Cancel" button designed and implemented.
|  | US-03 | As a user, I want to be able to cancel my event registration through the "Cancel" button. |  | Implement click functionality for the "Cancel" button. |  | Click functionality for "Cancel" button implemented. | 8 Hours
[5 empty] | Develop logic to send a cancellation request to the server using the selected request ID. |  | Logic for sending cancellation request with request ID functional.
[5 empty] | Upon successful cancellation, update the UI to reflect the cancelled status or redirect to a confirmation page. |  | UI update or redirection upon successful cancellation implemented.
[5 empty] | Implement error handling for unsuccessful cancellation attempts and display appropriate messages to the user. |  | Error handling for cancellation failures implemented with user-friendly messages.