## Backlog
Sprints |  | Stories |  | Task |  | CheckList |  | Est. Time
0 | setup
|  | US-01 | Folder Structure
|  | US-02 | Header
|  | US-03 | Footer
|  | US-04 | Navbar
|  | US-05 | Breadcrump
|  | US-06 | Sidebar
1 | My Requests
|  | US-01 | As logged user, I want to see a list of all my event registration requests in the "My Requests" section. | T-01 | Develop API calls to fetch user request data from ws_myrequests and request-status endpoints. | CL-01 | Sidebar is floating | 4 Hours
|  | US-02 | As a user, I want the "My Requests" section to be paginated for large numbers of requests | T-02 | Design and implement the "My Requests" section with pagination, filtering, and request details. | CL-02 | Date Range (From -to)
|  | US-03 | As a user, I want to filter my requests by request number, status, and submission date.
|  | US-04 | As a user, I want the "My Requests" section to display request number, status, and submission date for each Fliteration request
2 | Events Landing & Event details
|  | US-01 | As a user, I want to click on an "Events" link to see a list of upcoming events. (Events Landing) | T-01 | Develop API calls to fetch event data from events_category-listing and events_listing endpoints.
|  | US-02 | As a user, I want the Events Landing page to display event details like name, date, image, category, description, and location. (Events Landing) | T-02 | Design and implement the Events Landing page with filtering and sorting functionalities.
|  | US-03 | As a user, I want to see a maximum of 6 upcoming events with paging enabled for older events. (Events Landing) | T-03 | Design and implement the Event Details page with registration button. Implement logic to check for past events and disable registration.
|  | US-04 | As a user, I want to filter events by date, category, or available tickets. (Events Landing)
|  | US-05 | As a user, I want events to be sorted by date in ascending order. (Events Landing)
|  | US-06 | As a user, I want to click on an event name to see its detailed information on a separate page. (Event Details)
|  | US-07 | As a user, I want the Event Details page to display additional information like end date and event tickets. (Event Details)
|  | US-08 | As a user, I want a "Register Now" button to register for an event, redirecting me to the registration page. (Event Details)
|  | US-09 | As a user, I shouldn't be able to register for events that have already passed. (Event Details)
3 | Workspace Dashboard
3 | Registration Request details page